## Sheet1
SDLC Phase | Task ID | Task | Assigned To | Start Date | End Date | DAYS
Planning | T1 | Requirement Gathering & User Story Mapping | Ajit | 2025-09-01 | 2025-09-03 | 3
| T2 | Trello Setup & Backlog Creation | Sanjay | 2025-09-02 | 2025-09-04 | 3
System Design | T3 | UI/UX Wireframes & Prototype (Register/Login, Menu, Cart) | Karan | 2025-09-03 | 2025-09-08 | 6
Development | T4 | Backend Setup (Authentication, Database) | Ajit | 2025-09-05 | 2025-09-09 | 5
| T5 | Menu Display Feature (Frontend) | Sanjay | 2025-09-06 | 2025-09-09 | 4
| T6 | Cart & Order Placement Module | Karan | 2025-09-10 | 2025-09-14 | 5
| T7 | Secure Payment Integration | Ajit | 2025-09-11 | 2025-09-16 | 6
| T8 | Real-time Orders for Restaurant | Sanjay | 2025-09-12 | 2025-09-16 | 5
| T9 | Delivery Agent Dashboard | Karan | 2025-09-15 | 2025-09-18 | 4
| T10 | Admin Panel (User & Restaurant Management) | Ajit | 2025-09-17 | 2025-09-21 | 5
| T11 | Notifications & Order Tracking | Sanjay | 2025-09-18 | 2025-09-21 | 4
Test and deploy | T12 | Final Testing & Deployment | All Members | 2025-09-22 | 2025-09-26 | 5
Closure | T13 | Report Writing & PPT Prep | Ajit, Sanjay, Karan | 2025-09-27 | 2025-09-30 | 4